STATEMENT OF WORK – 21/may/2026

PROPOSED START DATE –  01/06/2026

| Site 1: | UQAM – Télétravail |  |  |  |
| --- | --- | --- | --- | --- |

Integrated Analysis of IoT, Behavioral and Environmental Data in Dairy Cattle, and Development of an IoT Demonstration Notebook, and Technical Support for WELL-E Toolkits

1. General Objectives

This project aims to leverage IoT data from accelerometer sensors attached to dairy cows’ legs, along with environmental data (temperature, humidity), to:

- advance the automatic detection of lameness using an already developed and validated pipeline,

- explore how environmental conditions influence locomotor behavior,

- assess whether behavioral observations should be incorporated into the models,

- develop a demonstration Notebook (e.g., Jupyter) showcasing IoT applications in dairy cattle management.

- Provide technical support for the development and use of WELL-E toolkits, including reviewing Python scripts converted from MATLAB and assisting in applying the toolkits in the context of Mira’s work.

2. Scope of Work

| Specific Aim 1: Apply and evaluate the existing lameness detection pipeline on new IoT data | Timeline |
| --- | --- |
| Major Task 1.1: Apply the validated pipeline to new accelerometer data | Semaines 1–2 (1–14 juin 2026) |
| Subtask 1 – Apply the pipeline (Isolation Forest + business rules, 15-min bins) to the 4 IceTag datasets: Fall 2019 (30 cows, T/C labels), Summer 2019 (18 cows), Winter 2019 (17 cows, SLS scores for 16/17), Fall 2021 (8 usable cows, Nov 30 to Dec 6 window only). |  |
| Subtask 2 – Generate lameness probability scores and alerts using existing thresholds/models. |  |
| Milestone: Pipeline successfully executed on the full dataset (with documented adaptation of input format). |  |
| Deliverables: - Processed dataset with predicted lameness alerts. - Technical note confirming pipeline reproducibility on new data. |  |
| Major Task 1.2: Compare automated alerts with cow behavioral observations | Semaines 3–4 (15–28 juin 2026) |
| Subtask 1 – Align pipeline alerts with behavioral scans. Summer 2019 and Winter 2019 use direct Cow_IDs. Fall 2019 and Fall 2021 use collar colours per paddock; a colour-to-Cow_ID mapping from McGill is required for these two. |  |
| Subtask 2 – Assess whether behavioral observations data could be integrated as an additional layer. |  |
| Milestone: Validation dataset created (alerts vs. behaviors). |  |
| Deliverables: - Concordance table (alerts vs cow behaviors). - Short validation report summarizing agreement patterns and limitations. |  |
| Specific Aim 2: Analyze the relationship between environmental conditions and locomotor behavior | Timeline |
| Major Task 2.1: Synchronize environmental and accelerometer data | Semaines 5–7 (29 juin–19 juil. 2026) |
| Subtask 1 – Inspect temporal resolution of environmental data and perform temporal alignment (synchronization, interpolation if needed). |  |
| Subtask 2 – Merge environmental, accelerometer, and behavior datasets. |  |
| Milestone: Fully synchronized multimodal dataset. |  |
| Deliverables: - Integrated dataset (accelerometers + environment + cow behaviors). - Documentation of synchronization procedure. |  |
| Major Task 2.2 : Conduct exploratory analyses on environment–behavior interactions | Semaines 8–9 (20 juil.–2 août 2026) |
| Subtask 1 – Analyze locomotor activity via accelerometers across temperature/humidity variations. |  |
| Subtask 2 – Evaluate whether cow behavioral observations should be included as covariates |  |
| Subtask 3 – Identify gaps and future modeling opportunities. |  |
| Milestone: Set of environment–behavior visualizations produced |  |
| Deliverables: - Exploratory analysis report. - Notes on feasibility of integrated modeling. |  |
| Specific Aim 3: Develop an IoT demonstration notebook for dairy cattle applications | Timeline |
| Major Task 3.1 : Build a structured Notebook | Semaines 10–12 (3–23 août 2026) |
| Subtask 1 – Design and develop a structured Jupyter notebook covering: data loading and preprocessing, pipeline execution on IceTag data, environment–behavior visualizations, and an interpretation guide for dairy cattle IoT data. |  |
| Milestone: Functional version of the Notebook produced |  |
| Deliverables: - Final Notebook + documentation. |  |
| Specific Aim 4: Provide technical support for the development and use of WELL-E toolkits | Timeline |
| Major Task 4.1 : Review and improve existing WELL-E scripts and toolkits | Semaine 13 (24–31 août 2026) |
| Subtask 1 – Review Python scripts converted from MATLAB to ensure correctness, readability, and consistency. |  |
| Subtask 2 – Propose improvements or refactoring where appropriate. |  |
| Milestone: First pass of script review completed with documented issues and recommendations. |  |
| Deliverables: - Annotated review of Python scripts. - Updated or cleaned-up scripts. |  |
| Major Task 4.2 : Support the application of WELL-E toolkits in the context of Mira | Semaine 13 (24–31 août 2026) |
| Subtask 1 – Assist Animal Science Team in applying the relevant WELL-E toolkits to Mira’s dataset. |  |
| Subtask 2 – Document best practices for using the toolkits in Mira’s context |  |
| Milestone: WELL-E toolkits successfully applied to Mira’s use case. |  |
| Deliverables: - Short technical note describing how the toolkits were applied in Mira’s context. - Troubleshooting guide or FAQ for common issues. |  |