STATEMENT OF WORK – 21/may/2026

PROPOSED START DATE – ??/??/2026

| Site 1: | UQAM ? |  |  |  |
| --- | --- | --- | --- | --- |

Integrated Analysis of IoT, Behavioral and Environmental Data in Dairy Cattle, and Development of an IoT Demonstration Notebook, and Technical Support for WELL-E Toolkits

1. General Objectives

This project aims to leverage IoT data from accelerometer sensors attached to dairy cows’ legs, along with environmental data (temperature, humidity), to:

- advance the automatic detection of lameness using an already developed and validated pipeline,

- explore how environmental conditions influence locomotor behavior,

- assess whether behavioral observations should be incorporated into the models,

- develop a demonstration Notebook (e.g., Jupyter) showcasing IoT applications in dairy cattle management.

- Provide technical support for the development and use of WELL-E toolkits, including reviewing Python scripts converted from MATLAB and assisting in applying the toolkits in the context of Mira’s work.

2. Scope of Work

| Specific Aim 1: Apply and evaluate the existing lameness detection pipeline on new IoT data | Timeline |
| --- | --- |
| Major Task 1.1: Apply the validated pipeline to new accelerometer data | Weeks |
| Subtask 1 – Run XXX on the new dataset. |  |
| Subtask 2 – Generate lameness probability scores and alerts using existing thresholds/models. |  |
| Milestone: Pipeline successfully executed on the full dataset without modification. |  |
| Deliverables: - Processed dataset with predicted lameness alerts. - Technical note confirming pipeline reproducibility on new data. |  |
| Major Task 1.2: Compare automated alerts with cow behavioral observations | Weeks |
| Subtask 1 – Align times between IoT alerts and behavioral observations and identify concordant, discordant, and ambiguous cases. |  |
| Subtask 2 – Assess whether behavioral observations data could be integrated as an additional layer. |  |
| Milestone: Validation dataset created (alerts vs. behaviors). |  |
| Deliverables: - Concordance table (alerts vs cow behaviors). - Short validation report summarizing agreement patterns and limitations. |  |
| Specific Aim 2: Analyze the relationship between environmental conditions and locomotor behavior | Timeline |
| Major Task 2.1: Synchronize environmental and accelerometer data | Weeks |
| Subtask 1 – Inspect temporal resolution of environmental data and perform temporal alignment (synchronization, interpolation if needed). |  |
| Subtask 2 – Merge environmental, accelerometer, and behavior datasets. |  |
| Milestone: Fully synchronized multimodal dataset. |  |
| Deliverables: - Integrated dataset (accelerometers + environment + cow behaviors). - Documentation of synchronization procedure. |  |
| Major Task 2.2 : Conduct exploratory analyses on environment–behavior interactions | Weeks |
| Subtask 1 – Analyze locomotor activity via accelerometers across temperature/humidity variations. |  |
| Subtask 2 – Evaluate whether cow behavioral observations should be included as covariates |  |
| Subtask 2 – Identify gaps and future modeling opportunities. |  |
| Milestone: Set of environment–behavior visualizations produced |  |
| Deliverables: - Exploratory analysis report. - Notes on feasibility of integrated modeling. |  |
| Specific Aim 3: Develop an IoT demonstration notebook for dairy cattle applications | Timeline |
| Major Task 3.1 : Build a structured Notebook | Weeks |
| Subtask 1 – |  |
| Milestone: Functional version of the Notebook produced |  |
| Deliverables: - Final Notebook + documentation. |  |
| Specific Aim 4: Provide technical support for the development and use of WELL-E toolkits | Timeline |
| Major Task 4.1 : Review and improve existing WELL-E scripts and toolkits | Weeks |
| Subtask 1 – Review Python scripts converted from MATLAB to ensure correctness, readability, and consistency. |  |
| Subtask 2 – Propose improvements or refactoring where appropriate. |  |
| Milestone: First pass of script review completed with documented issues and recommendations. |  |
| Deliverables: - Annotated review of Python scripts. - Updated or cleaned-up scripts. |  |
| Major Task 4.2 : Support the application of WELL-E toolkits in the context of Mira | Weeks |
| Subtask 1 – Assist Animal Science Team in applying the relevant WELL-E toolkits to Mira’s dataset. |  |
| Subtask 2 – Document best practices for using the toolkits in Mira’s context |  |
| Milestone: WELL-E toolkits successfully applied to Mira’s use case. |  |
| Deliverables: - Short technical note describing how the toolkits were applied in Mira’s context. - Troubleshooting guide or FAQ for common issues. |  |